## Sheet1
音声データ変換アプリケーションスケジュール
software schedule
| 項目 Item |  | 担当 Person in charge | July | [17 empty] | Aug | [30 empty] | Sep
|  |  |  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
|  |  |  | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6
| イベント |  | -
event
| 提案資料 |  | -
画面操作
| 要件定義書 |  | -
機能定義
| 設計書 |  | -
プログラム
| システム設計 |  | -
System design
|  | 仮仕様 | YAMASAKI
Pre Spec
|  | 量産向け仕様 | YAMASAKI
Mass production Spec
| 量産ソフトウェア設計 |  | -
Mass pro duction design
|  | 仕様書 | YAMASAKI
Spec document
|  | 設計書 | YAMASAKI
Design document
|  | モジュール仕様書 | THANG
Module spec
|  | コーディング | THANG
Coding
|  | 単体テスト | THANG
Unit test
|  | 結合テスト | TAN
Combined test
| バラック基板作成 |  | TAN
Barraque booard making
|  | システム用回路検討 | THANG
Circuit design (for system)
|  | 部材購入 | THANG,TAN
purchase
| 部材 |  | -
Parts
|  | マイク | TAN
Microphone
|  | マイコン | THANG
MCU
|  | アンプ | TAN
Amplifier
|  | スピーカー | TAN
Speaker
Spec = Specification
★T6 weekly
★T5 weekly
★T6 weekly
★T2 Submit 1st prototype software
★Estimated delivery
Design?
Document
DEJP holiday
★T6 weekly
★Submit
Coding
Not a mast?
Test
Changed to mass production specifications with reference to prototype
Redesign based on user feedback
★T2 Code check
Design
Document
Coding